## Timeline
CHAGEE AR Campaign
Model | Description | Kivisense | Brands | Status | [15 empty] | August | [20 empty] | September | [20 empty] | October
[5 empty] | 13 | 14 | 15 | 16 | 17 | 20 | 21 | 22 | 23 | 24 | 27 | 28 | 29 | 30 | 31 | 3 | 4 | 5 | 6 | 7 | 10 | 11 | 12 | 13 | 14 | 17 | 18 | 19 | 20 | 21 | 24 | 25 | 26 | 27 | 28 | 31 | 1 | 2 | 3 | 4 | 7 | 8 | 9 | 10 | 11 | 14 | 15 | 16 | 17 | 18 | 21 | 22 | 23 | 24 | 28 | 29 | 30 | 8 | 9 | 10 | 12 | 13
Requirement | Project Scope & Timeline Update | √ | bar: 13
| Project Scope & Timeline Confirmation |  | √ | bar: 13 to 14
Proposal | Proposal Update #Pocket Charista | √ | bar: 13 to 14
| Proposal Update #Mural | √ | bar: 15 to 17
| Feedback #Pocket Charista |  | √ | bar: 15 to 17
| Feedback #Mural |  | √ | bar: 20 to 22
| Adjustment #Pocket Charista | √ | bar: 20 to 24
| Adjustment #Mural | √ | bar: 23 to 29
| Confirmation #Pocket Charista |  | √ | bar: 27 to 31
| Confirmation #Mural |  | √ | bar: 30 to August 5
Technical Proposal | Technical Proposal Update | √ | bar: 23 to 24
| Feedback on Technical Proposal |  | √ | bar: 27 to 31
| Technical Proposal Adjustment | √ | bar: August 3 to August 5
| Technical Proposal Confirmation |  | √ | bar: August 6 to August 7
Video | Feedback #Shadow Box |  | √ | bar: 13 to 24
| Adjustment #Shadow Box | √ | bar: 27 to 31
| Confirmation #Shadow Box |  | √ | bar: August 3 to August 14
Design | UI / UX Update #Pocket Charista | √ | bar: August 3 to August 5
| UI / UX Update #Mural | √ | bar: August 6 to August 10
| Confirmation #Pocket Charista |  | √ | bar: August 6 to August 12
| Confirmation #Mural |  | √ | bar: August 11 to August 17
Development | Development #Vally Fair H5 | √ | bar: 27 to August 28
| Development #Other |  | √ | bar: August 10 to August 28
| Integration | √ | √ | bar: August 24 to August 28
| SIT | √ | bar: August 31 to September 11
UAT | UAT #Round 1 & Feedback |  | √ | bar: September 14 to September 16
| Adjustment | √ | bar: September 17 to September 18
| UAT #Round 2 & Feedback |  | √ | bar: September 21 to September 23
| Adjustment | √ | bar: September 24 to September 28
| Confirmation |  | √ | bar: September 28 to September 30
Launch | Launch | √ | bar: September 30